## Sheet1
Product Tasks | Broken Down Tasks | Assignment | Initial | M1 | M2 | M3
Display a list of current courses, allowing one to be selected | Create Query Function from model
View List as Bulleted Points
View as drop down list
Display details of a specific course | Create Query Function from model
Display in Paragraph Form
Display in Card Form
Display a list of training rooms, allowing one to be selected | Create Query Function from model
View List as Bulleted Points
View as drop down list
Display details of a specific training room | Create Query Function from model | [5 empty] | KEY
| Display in Paragraph Form | [5 empty] | Back End | Luke Roberts | Ben Reed
| Display in Card Form | [5 empty] | Front End | Jake Horsfield | Suhaib Saeed | Jacob Holland
Display details of a specific trainer | Create Query Function from model
Display in Paragraph Form
Display in Card Form
Create a course, specifying its title, a short description, duration (in days), the maximum number of delegates, any prerequisite courses | Create Database Model
Test Model
Create Form Model
Create form to add DB Entries
Add a training room, specifying its physical location (city and street address), type (computer lab, seminar room, etc), seating capacity, facilities (computer projection, etc), accessibility for the disabled | Create Database Model
Test Model
Create Form Model
Create form to add DB Entries
Add a trainer, specifying their name, home address, email address, phone number | Create Database Model
Test Model
Create Form Model
Implement form to add DB Entries